## 具体项目表
稀土高新区2026年政府投资5000万元以上、企业投资亿元以上重大项目表
序号 | 项目名称 | 项目 业主单位 | 建设内容及规模 | 投资 类型 | 建设 性质 | 总投资 | 2026年计划 完成投资 | 前期手续阶段 | [11 empty] | 备注
[8 empty] | 立项手续 | 建设工程文物保护和考古许可 | 用地预审和规划选址意见书 | 建设用地规划许可审批 | 建设工程规划许可审批 | 新增建设用地审批 | 节能手续 | 林地征占手续 | 草地征占手续 | 环境影响评价手续 | 取水许可手续 | 开工许可手续 （包括施工许可证、或行业主管部门批复的开工报告）
[8 empty] | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理 | 是否办理
1 | 金龙稀土新材料（包头）有限公司高性能稀土永磁材料项目 | 金龙稀土新材料（包头）有限公司 | 项目占地200亩，建设高性能稀土永磁材料智能化生产线及配套设施。 | 企业 投资 | 续建 | 20 | 10 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
2 | 包头市华宏新材料科技有限公司稀土永磁材料项目（一期） | 包头市华宏新材料科技有限公司 | 项目占地130亩，建设年产1万吨高性能稀土永磁材料生产线。 | 企业 投资 | 续建 | 20 | 5 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
3 | 包头韵升科技发展有限公司年产15000吨高性能稀土永磁材料智能制造项目 | 包头韵升科技发展有限公司 | 项目占地130亩，建设15000吨烧结钕铁硼磁材生产线及相应公辅设施。 | 企业 投资 | 续建 | 20 | 5 | 是 | 无需办理 | 无需办理 | 无需办理 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
4 | 包头市恒景房地产开发有限公司包头恒大珺庭项目 | 包头市恒景房地产开发有限公司 | 项目用地面积101610.3平方米，建设高层住宅楼、公寓、幼儿园、商业等。 | 企业 投资 | 续建 | 16.8 | 6 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是
5 | 金力永磁（包头）科技有限公司年产20000吨磁材项目 | 江西金力永磁科技股份有限公司 | 项目占地115亩，拟建设生产车间等主体建筑以及相应的供电、供水、供气等公辅设施，在已建成的20000万吨高性能稀土永磁材料产能的基础上，扩产建设高性能稀土永磁材料绿色智造生产线。 | 企业 投资 | 续建 | 16.5 | 6 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
6 | 卧龙控股集团有限公司稀土永磁电机项目 | 卧龙控股集团有限公司 | 项目占地200亩。新建低速大功率矿山用稀土永磁电机、超高速耐高温家电用永磁电机生产线及配套设施。 | 企业 投资 | 续建 | 12 | 1 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
7 | 高性能稀土永磁材料基地项目 | 金力永磁（包头）科技有限公司 | 项目占地203亩，新建年产10000吨高性能烧结钕铁硼及深加工产品生产线及配套设施。 | 企业 投资 | 续建 | 12 | 3 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
8 | 国能铁路装备有限责任公司新建包头维修中心工程项目 | 国能铁路装备有限责任公司 | 项目占地约445亩，新建客运大机装配、检修、编组线兼试验线及设施设备。 | 企业 投资 | 续建 | 11.05 | 3 | 是 | 无需办理 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 是 | 是 | 是 | 无需办理
9 | 北方稀土磁材公司年产5万吨高性能钕铁硼速凝合金项目 | 北方稀土磁性材料有限公司 | 项目占地98.12亩，新建年产50000吨钕铁硼速凝薄带合金生产线及配套设施。 | 企业 投资 | 续建 | 10.2 | 2.2 | 是 | 无需办理 | 无需办理 | 无需办理 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
10 | 包头滨河置业有限责任公司水岸花都住宅小区三期项目 | 包头滨河置业有限责任公司 | 项目建设高端住宅，建筑面积116821平方米，其中地下车库建筑面积22647平方米，14栋住宅楼，1座幼儿园。 | 企业 投资 | 续建 | 5 | 2 | 是 | 无需办理 | 是 | 是 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是
11 | 内蒙古自治区高层次人才创新创业基地提升改造项目 | 稀土高新区科技创新局 | 项目对海创大厦及6栋生产厂房进行改造，运营盘活闲置场地，引进高层次人才，推动稀土纳米断热材料、稀土红外反射中空隔热聚酰胺纤维技术等先进技术落地转化，打造高能级高层次人才创新创业基地。 | 政府 投资 | 续建 | 5 | 2.3 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
12 | 包头韵升强磁材料有限公司年产6000吨高端装备及轨道交通用稀土永磁材料扩产项目 | 包头韵升强磁材料有限公司 | 项目扩建烧结钕铁硼磁材生产线及优化公辅设施。 | 企业 投资 | 续建 | 3.8 | 2 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理
13 | 内蒙古天石科技发展有限公司年产16000吨高端稀土基复合功能材料及7000吨稀土化合物项目 | 内蒙古天石科技发展有限公司 | 项目租赁科电电气5400㎡厂房，新建年产10000吨高端稀土基复合催化剂生产线及配套设施。 | 企业 投资 | 续建 | 3 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
14 | 包头麦戈龙科技有限公司新建年产3000吨高性能烧结钕铁硼多级辐射电机磁环生产项目 | 包头麦戈龙科技有限公司 | 项目建设年产3000吨高性能烧结钕铁硼多级辐射电机磁环。 | 企业 投资 | 续建 | 2 | 1 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 是
15 | 日本相模磁业公司年产5000吨钕铁硼永磁组件及绿色智能化项目 | 日本相模化学金属株式会社 | 项目占地60亩，建设生产能力5000吨/年的高性能钕铁硼磁体生产线。 | 企业 投资 | 续建 | 1.6 | 0.6 | 是 | 是 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
16 | 德国库门瑙尔公司矿用电机制造项目 | 德国库门瑙尔公司 | 项目租赁爱科风机2300㎡厂房，新建矿用电机生产线及配套设施。 | 企业 投资 | 续建 | 1.6 | 0.7 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
17 | 包头北方中加特电气有限公司北方中加特稀土永磁高效电机项目 | 包头北方中加特电气有限公司 | 项目租赁厂房14106.5平方米，建设电机装配、机械加工等工艺的年产5500台永磁变频一体机智能化生产线及配套设施。 | 企业 投资 | 续建 | 1.3 | 0.8 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
18 | 内蒙古中天宏远稀土新材料股份公司设备绿色智能化升级改造项目 | 内蒙古中天宏远稀土新材料股份公司 | 项目对原有熔炼炉设备、砂处理系统、电控系统、锻轧设备进行自动化智能化绿色化升级改造。 | 企业 投资 | 续建 | 1.2 | 1.2 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
19 | 辽宁抚顺煤矿电机公司年产2500台矿用电机项目 | 辽宁抚顺煤矿电机公司 | 项目租用E1厂房4500㎡，新建年产2500台矿用电机生产线。 | 企业 投资 | 续建 | 1.37 | 1.37 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
20 | 包头天之和磁材设备制造有限公司高性能稀土永磁生产设备制造与研发项目 | 包头天之和磁材设备制造有限公司 | 项目一期占地67亩，建设高性能稀土永磁生产设备制造与研发生产线及相应公辅设施。 | 企业 投资 | 续建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 否 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
21 | 时代广场房地产项目 | 包头市方兴置家房地产开发有限公司 | 项目位于稀土高新区黄河大街以南、阿尔丁大街以东，占地245亩，建设高端住宅小区项目。 | 企业 投资 | 新建 | 40 | 15 | 否 | 无需办理 | 无需办理 | 否 | 否 | 是 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否
22 | 远景集团风电产业园项目 | 远景能源有限公司 | 项目位于滨河新区，一期占地200亩，建设18GW大兆瓦风电主机生产线。 | 企业 投资 | 新建 | 25 | 15 | 否 | 无需办理 | 无需办理 | 否 | 否 | 是 | 否 | 是 | 是 | 否 | 否 | 无需办理
23 | 华电包头风光氢储高端装备智造项目 | 内蒙古华电腾格里绿色能源有限公司包头智能装备制造分公司 | 项目建设氢能高端装备制造、储能装备制造、风机叶片循环利用、风电装备制造、光伏装备制造生产基地。 | 企业 投资 | 新建 | 20 | 7 | 是 | 无需办理 | 无需办理 | 是 | 否 | 是 | 否 | 是 | 是 | 无需办理 | 否 | 无需办理
24 | 金龙稀土股份有限公司15000吨高性能稀土永磁材料项目（二期） | 金龙稀土新材料（包头）有限公司 | 项目占地200亩，建设15000吨高性能钕铁硼磁性材料生产线，包括3栋主体厂房。 | 企业 投资 | 新建 | 15 | 15 | 否 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
25 | 英思特稀磁公司稀土永磁应用一体化项目 | 包头市英思特稀磁新材料股份有限公司 | 项目位于永磁电机产业园，占地207亩，建设稀土永磁应用一体化生产线及配套设施。 | 企业 投资 | 新建 | 10 | 2.8 | 是 | 无需办理 | 无需办理 | 是 | 是 | 是 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
26 | 瑞声科技20000吨异形磁材项目 | 瑞声科技控股有限公司 | 项目拟租用永磁电机产业园厂房，建设年产20000吨异形磁材生产线及相应公辅设施。 | 企业 投资 | 新建 | 10 | 2 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
27 | Ti-car汽车主题特色街区 | 内蒙古阿斯创实业有限公司 | 项目打造西北地区首家以汽车为主题，集汽车销售、汽车文化、科技互动、生活社交、旅游休闲、商业配套于一体的新一代产城融合特色街区。 | 企业 投资 | 新建 | 10 | 6.5 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
28 | 包头天和新材料科技有限公司高性能稀土永磁及组件、装备制造与研发项目 | 包头天和新材料科技有限公司 | 项目占地200亩，建设稀土永磁材料项目。 | 企业 投资 | 新建 | 8.5 | 6 | 是 | 无需办理 | 是 | 是 | 是 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
29 | 宁波铄腾新材料有限公司与北方稀土年产1万吨稀土磁材项目（一期） | 宁波铄腾新材料有限公司 | 项目占地100亩，建设年产1万吨稀土磁材生产线。 | 企业 投资 | 新建 | 5 | 5 | 否 | 无需办理 | 无需办理 | 否 | 否 | 否 | 否 | 无需办理 | 无需办理 | 否 | 否 | 无需办理
30 | 宁波金轮磁材技术有限公司年产5000吨稀土磁性材料项目 | 宁波金轮磁材技术有限公司 | 项目建设年产5000吨稀土永磁材料生产线及相应公辅设施。 | 企业 投资 | 新建 | 5 | 3 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
31 | 零碳园区智慧能碳管理监测平台 | 远景能源有限公司 | 项目通过精准预测，实现绿色能源供给与企业用能需求的最佳匹配，最大限度地就地消纳可再生能源；平台是实施需求响应、削峰填谷等管理措施的技术核心，能帮助园区在电力市场中获得收益；智能调配园区的电、热、冷、气、氢等多种能源，实现综合能效的最优化；监控和记录水、固废等资源的循环利用数据，为任务四的指标达成提供量化证明。 | 企业 投资 | 新建 | 5 | 2 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
32 | 有研半导体硅材料股份公司年产1000吨大尺寸半导体硅单晶项目 | 有研半导体硅材料股份公司 | 项目位于稀土高新区，建设单晶厂房、集成电路用硅单晶生产线、配套动力站、废水站、仓库、气站等，建设达产后可年产约1000吨半导体硅单晶，满足制造半导体12英寸硅片及半导体零部件需要。 | 企业 投资 | 新建 | 15 | 5 | 否 | 无需办理 | 无需办理 | 否 | 否 | 无需办理 | 否 | 无需办理 | 无需办理 | 否 | 否 | 无需办理
33 | 华硅（内蒙古）新材料科技有限公司年产2万吨超高纯石英砂和15万只石英坩埚项目 | 华硅（内蒙古）新材料科技有限公司 | 项目租用日新智谷厂房，主要建设内容为1.5万吨超高纯石英砂、15万吨石英坩埚产线。 | 企业 投资 | 新建 | 4 | 2 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
34 | 包头市雄盛光电科技有限公司稀土发光材料及LED照明项目 | 包头市雄盛光电科技有限公司 | 项目位于稀土高新区，建设内容为建设稀土发光材料、LED电子照明设备、电子显示屏生产线。 | 企业 投资 | 新建 | 1 | 1 | 否 | 无需办理 | 无需办理 | 否 | 否 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理
35 | 江苏华宏科技股份有限公司1万吨稀土磁材项目（二期） | 江苏华宏科技股份有限公司 | 项目位于滨河新区，占地130亩，扩建1万吨永磁材料生产线。 | 企业 投资 | 新建 | 4 | 1 | 否 | 无需办理 | 无需办理 | 是 | 是 | 是 | 否 | 无需办理 | 无需办理 | 是 | 否 | 无需办理
36 | 郑州天一萃取科技有限公司年产2T同位素锂7分离纯化项目 | 内蒙古锂核赛文科技有限公司 | 项目建设年产2T同位素锂7分离纯化生产线及相应公辅设施。 | 企业 投资 | 新建 | 3.6 | 3 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
37 | 宁波复能新材料股份有限公司与北方稀土年产1万吨高纯金属项目（一期） | 宁波复能新材料股份有限公司 | 项目占地90亩，建设高纯稀土金属材料生产线。 | 企业 投资 | 新建 | 3 | 3 | 否 | 无需办理 | 无需办理 | 否 | 否 | 是 | 否 | 是 | 是 | 否 | 否 | 无需办理
38 | 包头科田磁业有限公司年产4000吨高端制造高性能稀土永磁材料及器件项目（二期） | 包头科田磁业有限公司 | 项目占地130亩，拟新建年产4000吨高端制造高性能稀土永磁材料及器件生产线及配套设施。 | 企业 投资 | 新建 | 3 | 2 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
39 | 双良硅材料（包头）有限公司单晶炉干泵升级改造项目 | 双良硅材料（包头）有限公司 | 项目建设包括升级改造3072台1302型干式真空泵。通过采购4200型干泵，改造干泵匹配信号线及软件控制系统，改造真空管道接口，以干泵升级解决单品硅片氧含量控制难题，抢占N型低氧硅片高端市场，提升产品竞争力。 | 企业 投资 | 新建 | 3 | 2 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
40 | 深圳市新思路科技有限公司触控显示封装一体化北方制造基地项目 | 深圳市新思路科技有限公司 | 项目建设触控显示封装一体化北方制造基地。 | 企业 投资 | 新建 | 3 | 2 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
41 | 东方希望包头稀土铝业有限责任公司电解槽节能降碳技术改造 | 东方希望包头稀土铝业有限责任公司 | 项目对电解铝生产全流程智能化升级与绿色低碳技术改造。 | 企业 投资 | 新建 | 2.9 | 1.3 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
42 | 包头天和磁材科技股份有限公司12000吨磁材深加工及磁性材料组件项目 | 包头天和磁材科技股份有限公司 | 项目建设注塑工序与表面处理厂房、公辅设施建设引进注塑机、粉末成型压机、机械手、热烘道、充磁机等生产设备配套建设磷化、环氧、发蓝、倒角等表面处理产线建设纯水系统、污水处理设施及环保废气处理系统。 | 企业 投资 | 新建 | 2.5 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 否 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
43 | 黄河110kV输变电工程/金力永磁110kV变电站用户接网工程 | 包头供电分公司 | 项目新建110kV变电站一座，敷设110kV，YJLW03-630电缆13.8KM/敷设110kV，YJLW03-630电缆12KM。 | 企业 投资 | 新建 | 2.5 | 1.5 | 是 | 无需办理 | 无需办理 | 是 | 是 | 无需办理 | 否 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
44 | 高新技术等离子（风光储用）电火灶产学研综合基地项目 | 海南伊众福投资发展有限公司 | 项目租赁厂房稀土高新区稀土新材料产业基地10#厂房，面积约6000平方米，建设等离子风光储电火灶生产线六条，研发实验研发中心、综合办公室以及仓储材料产品库等。 | 企业 投资 | 新建 | 2.3 | 2.3 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
45 | 东方希望包头稀土铝业有限责任公司电解铝厂烟气无组织治理项目 | 包头希望铝业有限责任公司 | 新建备份脱硫塔并优化现有系统，强化总排风机工况控制；通过提升电解槽密闭性与排烟精细化控制降低排放；替换易损部件、优化电极工艺，并采用自动化出铝技术，减少无组织排放与固废产生。 | 企业 投资 | 新建 | 2.3 | 1.34 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
46 | 盛世恒通汽车产业园项目 | 内蒙古盛世恒通旧机动车交易市场有限责任公司 | 项目新建销售展厅25000平米及2万平米地下停车场。 | 企业 投资 | 新建 | 2 | 2 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
47 | 煜升科技年产2000台（套）柠条平茬机等高端农机装备项目 | 煜升科技有限公司 | 项目建设年产2000台（套）柠条平茬机等高端农机装备生产线及相应公辅设施。 | 企业 投资 | 新建 | 2 | 1 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 否 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
48 | 双良新能科技（包头）有限公司光伏产业园30MW分布式屋顶光伏项目 | 内蒙古泰富能源有限公司 | 项目分为四个子项目，每个子项目共由2个光伏发电分系统组成。电站暂选用545Wp单晶硅组件，每26块组件为一个光伏组件串，逆变器为300kW组串逆变器，9个或10个逆变器组成一个方阵，方阵采用3000kVA或者3200kVA箱变，光伏发电单元汇集为2回10kV集电线路接入到厂区10kV配电室，再通过并网柜接入配电系统，产生电量全额自发自用。建设周期12个月。 | 企业 投资 | 新建 | 2 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
49 | 深圳市汇川技术股份有限公司稀土永磁电机项目 | 深圳市汇川技术股份有限公司 | 项目租赁稀土高新区永磁电机产业园厂房，建设稀土永磁电机生产线。 | 企业 投资 | 新建 | 2 | 2 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
50 | 中伟新材料公司年产1万吨稀土磁材项目 | 中伟新材料公司 | 项目占地约89亩，新建年产10000吨高端制造高性能稀土永磁材料生产线及配套设施。 | 企业 投资 | 新建 | 2 | 1.5 | 是 | 是 | 无需办理 | 否 | 否 | 是 | 否 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理
51 | 包头华腾新材料有限公司5000吨中重稀土金属 | 包头华腾新材料有限公司 | 项目租赁贵鑫科技厂房，新建年产5000吨中重稀土金属和稀土合金生产线。 | 企业 投资 | 新建 | 2 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
52 | 江苏嘉轩智能工业科技股份有限公司永磁智能驱动设备项目 | 江苏嘉轩智能工业科技股份有限公司 | 项目租赁D2、E2厂房，建设油田钻顶驱电机项目，同步建设装配设备与实验设备；建设500套工业永磁改造电机和变频器项目。 | 企业 投资 | 新建 | 2 | 2 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
53 | 宁波尼兰德磁业有限公司3000吨磁材及深加工项目 | 宁波尼兰德磁业有限公司 | 项目建设年产3000吨磁材及深加工生产线及相应公辅设施。 | 企业 投资 | 新建 | 2 | 1.5 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
54 | 包头长安永磁电机有限公司超高音速飞行器舵机负载模拟器低惯量高动态响应永磁电机系统开发 | 包头长安永磁电机有限公司 | 项目建设超高音速飞行器舵机负载模拟器低惯量高动态响应永磁电机生产线。 | 企业 投资 | 新建 | 2 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
55 | 内蒙古喜凯隆新材料有限公司技改增效绿色节能项目 | 内蒙古喜凯隆新材料有限公司 | 项目建设内容：1.在现有车间增加两台套均质炉设备（包括35T均质炉体、冷却室、三维台车等公辅设施；2.增加破碎、撕碎、筛选、打包、压饼及辅助设施，年产10万吨绿色循环再生铝加工项目。3.原有生产车间加装一台套炒灰机。 | 企业 投资 | 新建 | 2 | 0.5 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
56 | 内蒙古青宾物业管理有限公司包头青宾食材冷链供应链基地暨平台项目 | 内蒙古青宾物业管理有限公司 | 项目占地约60亩，建设特殊温区冷冻冷藏区、冷链供应链和配送区、生鲜食材以及综合配套区等。 | 企业 投资 | 新建 | 1.9 | 1 | 是 | 无需办理 | 无需办理 | 否 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
57 | 包头稀土高新区四道沙河（红旗大桥南）液压坝建设工程、科技路南段雨水排口综合整治及昆河白云路排口整治项目 | 稀土高新区资源环境局 | 项目建设内容为：①液压坝主题工程②卸空管线工程③2#泵站改造工程④下泄通道改造工程⑤防渗工程。科技路南段雨水排口综合整治项目建设内容为：在科技路与沼潭南路交叉口北侧拟新建一座最大蓄水能力30万立方米,有效调蓄水能力20万立方米的调蓄池。昆河白云路排口整治项目建设内容为:拟建1座4.5万m2的钢筋混凝土调蓄池,内放潜水泵2个。 | 政府 投资 | 新建 | 1.7 | 0.6 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
58 | 包头中晟汽车高端品牌新能源汽车商城项目 | 包头中晟汽车销售服务有限公司 | 项目建设3000㎡的品牌展销中心、智能充电、二手车及置换市场。 | 企业 投资 | 新建 | 1.5 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
59 | 包头市泓程贸易有限公司阿维塔汽车4S店及附属用房项目 | 包头市泓程贸易有限公司 | 项目总建筑面积约4000平米，引进长安汽车高端品牌阿维塔，建设汽车展厅及汽车车维修厂等配套附属设施，扩大经营规模。 | 企业 投资 | 新建 | 1.5 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
60 | 内蒙古翊源实业有限公司万泉汇农贸综合市场 | 内蒙古翊源实业有限公司 | 项目占地约40余亩，建筑面积约40000平方米，建设2至3层局部5层钢筋混凝土结构农贸市场，按功能划分为商品储藏区和商品交易区。 | 企业 投资 | 新建 | 1.5 | 0.6 | 是 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
61 | 科海置业总部经济园区商改住房地产开发项目 | 包头市科海置业有限责任公司 | 项目占地32亩，新建商改住房地产开发。 | 企业 投资 | 新建 | 3 | 1 | 否 | 无需办理 | 无需办理 | 否 | 否 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否
62 | 内蒙古中科宏特高新科技有限责任公司高性能稀土功能吸波材料项目 | 内蒙古中科宏特高新科技有限责任公司 | 项目位于永磁电机产业园A3，项目建设1条年产50吨稀土红外隐身材料生产线及实验室。 | 企业 投资 | 新建 | 1.2 | 1.2 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
63 | 稀土高新区雨水管网改造提升工程 | 稀土高新区建设管理局 | 项目改造雨水管线全长25221米，管材为预应力钢筋混凝土管。其中，改造DN600雨水管线10854米；改造DN800雨水管线3600米；改造DN1000雨水管线1345米；改造DN1200雨水管线1185米；改造DN1400雨水管线3800米；改造DN1400雨水管线3800米；改造DN1600雨水管线1500米；改造1600x1400雨水盖板涵577米；改造2400x1600雨水盖板涵579米；改造2600x1800雨水盖板涵980米；改造2600x1600雨水盖板涵741米。 | 政府 投资 | 新建 | 1.123 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是
64 | 百正创源智能传动有限公司矿用智能卡轨车项目 | 百正创源智能传动有限公司 | 项目租赁永磁电机产业园A2厂房，建设矿用智能卡轨车生产线并配套公辅设施。 | 企业 投资 | 新建 | 1.1 | 1.1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
65 | 海平面高分子公司年产15万吨片碱项目 | 海平面高分子公司 | 项目占地6700平米。新建片碱机切片生产线。 | 企业 投资 | 新建 | 1.1 | 0.8 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
66 | 鹿城实验室创新能力建设项目 | 鹿城实验室 | 项目计划购置先进设备，提升科研创新能力，助力两个稀土基地建设。 | 政府 投资 | 新建 | 1 | 1 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
67 | 稀土新材料技术创新中心应用示范及平台建设项目 | 内蒙古北方稀土新材料技术创新有限公司 | 项目采用先进设备，提升科研创新能力，助力两个稀土基地建设。 | 企业 投资 | 新建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
68 | 中科蒙稀新材料有限责任公司年产8000吨高纯稀土功能材料项目 | 中科蒙稀半导体材料有限责任公司 | 项目建设年产8000T高端纯稀土化合物生产线及相应公辅设施。 | 企业 投资 | 新建 | 1 | 0.8 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理
69 | 珠海格力电器股份有限公司高端电磁线项目 | 珠海格力电器股份有限公司 | 项目租赁永磁电机产业园D1厂房，建设高端电磁线生产线。 | 企业 投资 | 新建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
70 | 内蒙古沸石山稀晶高新科技有限公司稀土化合物、稀土微肥生产线建设项目 | 内蒙古蒙稀超分子新材料科技有限公司 | 项目建设稀土化合物、稀土微肥生产线及相应公辅设施 | 企业 投资 | 新建 | 1 | 1 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理
71 | 内蒙古稀金稀土新材料有限公司10000吨稀土精炼剂、铝金属添加剂生产制造项目 | 内蒙古稀金稀土新材料有限公司 | 项目租赁机电园区内蒙古金沃重力设备制造有限公司厂房，建年产10000吨稀土精炼剂和铝金属添加剂产品产线。 | 企业 投资 | 新建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理
72 | 北方稀土稀土高能级科技创新平台 | 北方稀土科技有限公司 | 项目建设规模约10万㎡，地下24000㎡。 | 企业 投资 | 新建 | 7 | 3.5 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
73 | 卧龙电驱（包头）永磁电机有限公司300kW高功率密度轴向磁通永磁同步电机关键技术研究 | 卧龙电驱（包头）永磁电机有限公司 | 项目利用原有厂房建设年产100台高功率密度轴向磁通永磁同步电机的中试线。 | 企业 投资 | 新建 | 1 | 1 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
74 | 包头金储智慧新能源有限公司金风包头金储智慧新能源储能项目 | 包头金储智慧新能源有限公司 | 项目占地约90亩，建设储能生产线。 | 企业 投资 | 新建 | 1 | 0.7 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
75 | 郑州天一萃取科技有限公司新型高效稀土永磁离心萃取装备制造项目 | 郑州天一萃取科技有限公司 | 项目建设新型高效稀土永磁离心萃取装备制造生产线及相应公辅设施。 | 企业 投资 | 新建 | 1 | 1 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
76 | 铂鑫金属制造（包头）有限公司年产3000吨不锈钢基材表面处理项目 | 铂鑫金属制造（包头）有限公司 | 项目建设年产3000吨不锈钢基材表面处理生产线。 | 企业 投资 | 新建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
77 | 包头市光科激光技术有限责任公司激光增材制造项目 | 包头市光科激光技术有限责任公司 | 项目位于建成区，建设激光增材制造专用厂房，包括原材料存储区、激光加工区、后处理区、检测区等功能分区，配备先进的激光增材制造设备，形成从设计到成品的完整生产线。 | 企业 投资 | 新建 | 1.02 | 1.02 | 是 | 无需办理 | 无需办理 | 无需办理 | 是 | 无需办理 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
78 | 中影产业发展集团（海南）有限公司华住会旗下海友酒店、汉庭酒店、桔子酒店和中影灯塔影院项目 | 中影产业发展集团（海南）有限公司 | 项目利用信德慧等建筑改造，建设3000㎡酒店。 | 企业 投资 | 新建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
79 | 上恒嗵(内蒙古)汽车销售服务有限公司上恒嗵汽车城项目 | 上恒嗵(内蒙古)汽车销售服务有限公司 | 项目占地30亩，建设汽车展厅、汽车维修车间、充电站、二手车出口业务大厅及其它附属设施。 | 企业 投资 | 新建 | 1 | 1 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
80 | 稀土高新区雁翔路南侧城市危旧房改造项目（二期） | 稀土高新区建设管理局 | 项目拆除重建危旧房35处，改造危旧房23处。改造居住区内改造公益性基础设施、社区综合服务，改建文化体育、适老化等便民公共服务设施，改造提升加固危旧房，拆除重建危旧房，平房院落修缮、修建等配套设施。 | 政府 投资 | 新建 | 0.8505 | 0.55 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 是
81 | 幸福南路老旧片区配套基础设施改造工程 | 稀土高新区建设管理局 | 项目建设内容：1.高新区平房区。为改善周边环境提高周边居民生活质量，计划改造该区域基础设施。主要内容包括排水、供水、供热、道路、照明等公共服务设施。主要工程量包括：道路及硬化13408平方米、给水管线5546米、污水管线1641米、雨水管线425米、新建供热二次网6560米、供热入户管8976米，换热站1座等。2.对幸福南路周边区域的老旧设施进行改造，计划改造雨水管线180米及道路和硬化恢复；对区域周边两条断头路进行改造改造面积10000平方米；对区域周边绿化水管线进行改造。3.小区安全隐患整治工程，对存在楼体外墙和附属构筑物脱落、存在消防隐患、存在外墙倾斜的小区进行集中整治。对檀香湾在内的11个小区进行楼体安全隐患治理，对鹿港小镇在内的5个小区的消防设施进行集中整治。计划建设7个完整社区。 | 政府 投资 | 新建 | 0.5767 | 0.5 | 否 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理
82 | 北师大包头附校综合文体活动中心、体育馆改建项目 | 稀土高新区社会事务局 | 项目对北师大包头附校现有体育馆、游泳馆进行改建，改建面积6758㎡及设施设备等配置。 | 政府 投资 | 新建 | 0.5 | 0.5 | 是 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理 | 无需办理

## 汇总
附件1-1 | [34 empty] | 附件1-2 | [33 empty] | 附件1-3
2026年重大项目分旗县区、部门汇总表 | [34 empty] | 2026年重大项目分旗县区、部门汇总表（续建） | [33 empty] | 2026年重大项目分旗县区、部门汇总表（新建）
[33 empty] | 单位:亿元、个 | [33 empty] | 单位:亿元、个 | [33 empty] | 单位:亿元、个
地区部门 |  | 总体情况 |  |  | 截至目前进度 |  |  |  | 立项手续 |  | 建设工程文物保护和考古许可 |  | 用地预审和规划选址意见书 |  | 建设用地规划许可审批 |  | 建设工程规划许可审批 |  | 新增建设用地审批 |  | 节能手续 |  | 林地征占手续 |  | 草地征占手续 |  | 环境影响评价手续 |  | 取水许可手续 |  | 施工许可证手续 |  | 11项手续齐全项目数 |  | 地区部门 | 总体情况 |  |  | 截至目前进度 |  |  |  | 立项手续 |  | 建设工程文物保护和考古许可 |  | 用地预审和规划选址意见书 |  | 建设用地规划许可审批 |  | 建设工程规划许可审批 |  | 新增建设用地审批 |  | 节能手续 |  | 林地征占手续 |  | 草地征占手续 |  | 环境影响评价手续 |  | 取水许可手续 |  | 施工许可证手续 |  | 11项手续齐全项目数 |  | 地区部门 | 总体情况 |  |  | 截至目前进度 |  |  |  | 立项手续 |  | 建设工程文物保护和考古许可 |  | 用地预审和规划选址意见书 |  | 建设用地规划许可审批 |  | 建设工程规划许可审批 |  | 新增建设用地审批 |  | 节能手续 |  | 林地征占手续 |  | 草地征占手续 |  | 环境影响评价手续 |  | 取水许可手续 |  | 施工许可证手续 |  | 11项手续齐全项目数
|  | 项目数 | 总投资 | 年内计划投资 | 开复工数 | 开复工率 | 完成投资 | 完成 投资率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 |  | 项目数 | 总投资 | 年内计划投资 | 开复工数 | 开复工率 | 完成投资 | 完成 投资率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 |  | 项目数 | 总投资 | 年内计划投资 | 开复工数 | 开复工率 | 完成投资 | 完成 投资率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率
全市合计 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 全市合计 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 全市合计 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
昆区 | 昆区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 昆区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 昆区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
青山区 | 青山区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 青山区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 青山区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
东河区 | 东河区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 东河区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 东河区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
九原区 | 九原区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 九原区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 九原区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
石拐区 | 石拐区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 石拐区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 石拐区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
白云矿区 | 白云 矿区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 白云矿区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 白云矿区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
土右旗 | 土右旗 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 土右旗 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 土右旗 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
达茂旗 | 达茂旗 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 达茂旗 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 达茂旗 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
固阳县 | 固阳县 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 固阳县 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 固阳县 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
高新区 | 高新区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 高新区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 高新区 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市城管局 | 市级-城管局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市城管局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市城管局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市交通局 | 市级-交通局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市交通局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市交通局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市教育局 | 市级-教育局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市教育局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市教育局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市生态环境局 | 市级-生态环境局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市生态环境局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市生态环境局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市水务集团 | 市级-水务集团 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市水务集团 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市水务集团 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市公安局 | 市级-公安局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市公安局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市公安局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市卫健委 | 市级-卫健委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市卫健委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市卫健委 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市自然资源局 | 市级-自然资源局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市自然资源局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市自然资源局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市水务局 | 市级-水务局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市水务局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市水务局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市政数局 | 市级-政数局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市政数局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市政数局 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
市文旅集团 | 市级-文旅集团 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市文旅集团 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 市文旅集团 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
部门项目合计 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 部门项目合计 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 部门项目合计 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 分行业
| 2025年重大项目分行业汇总表 | [33 empty] | 2025年重大项目分行业汇总表（续建） | [33 empty] | 2025年重大项目分行业汇总表（新建）
[33 empty] | 单位:亿元、个 | [33 empty] | 单位:亿元、个 | [33 empty] | 单位:亿元、个
行业 |  | 总体情况 |  |  | 截至目前进度 |  |  |  | 立项手续 |  | 建设工程文物保护和考古许可 |  | 用地预审和规划选址意见书 |  | 建设用地规划许可审批 |  | 建设工程规划许可审批 |  | 新增建设用地审批 |  | 节能手续 |  | 林地征占手续 |  | 草地征占手续 |  | 环境影响评价手续 |  | 取水许可手续 |  | 施工许可证手续 |  | 11项手续齐全项目数 |  | 地区部门 | 总体情况 |  |  | 截至目前进度 |  |  |  | 立项手续 |  | 建设工程文物保护和考古许可 |  | 用地预审和规划选址意见书 |  | 建设用地规划许可审批 |  | 建设工程规划许可审批 |  | 新增建设用地审批 |  | 节能手续 |  | 林地征占手续 |  | 草地征占手续 |  | 环境影响评价手续 |  | 取水许可手续 |  | 施工许可证手续 |  | 11项手续齐全项目数 |  | 地区部门 | 总体情况 |  |  | 截至目前进度 |  |  |  | 立项手续 |  | 建设工程文物保护和考古许可 |  | 用地预审和规划选址意见书 |  | 建设用地规划许可审批 |  | 建设工程规划许可审批 |  | 新增建设用地审批 |  | 节能手续 |  | 林地征占手续 |  | 草地征占手续 |  | 环境影响评价手续 |  | 取水许可手续 |  | 施工许可证手续 |  | 11项手续齐全项目数
|  | 项目数 | 总投资 | 年内计划投资 | 开复工数 | 开复工率 | 完成投资 | 完成 投资率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 |  | 项目数 | 总投资 | 年内计划投资 | 开复工数 | 开复工率 | 完成投资 | 完成 投资率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 |  | 项目数 | 总投资 | 年内计划投资 | 开复工数 | 开复工率 | 完成投资 | 完成 投资率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率 | 办结数 | 办结率
全市合计 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 全市合计 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 全市合计 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
工业 | 工业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 工业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 工业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
服务业 | 服务业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 服务业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 服务业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
农牧业 | 农牧业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 农牧业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 农牧业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
房地产 | 房地产 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 房地产 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 房地产 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
基础设施 | 基础 设施 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 基础设施 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 基础设施 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
社会事业 | 社会 事业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 社会事业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 社会事业 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
生态环保 | 生态 环保 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 生态环保 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 生态环保 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!